## Activity Schedule Instructions
Activity Schedule Instructions
1. The schedule provided is the template and format that must be submitted by the bidder. The activity schedule will be used for cashflow forecasting, payment milestone and payment triggers. The bidder shall accept full responsibility for the correctness of the activity schedule and its contents submitted.
2. It is the bidders responsibility to ensure that all activities or tasks are included and accounted for on the activity schedule.
3. The bid is for a fixed and firm offer , meaning, the bidder must also include for all costs fo the risks anticipated within the contingency line item- as the total price offered will not be varied or escalated for the 5 month duration allowed on the project.
4. If the bidder qualifies any portion of the bid which may have a time or cost impact , the bid shall be deemed to have not met the fixed and firm price criteria. It is not recommended for bidders to exclude or qualify any items.
5. Should the bidder fail to achieve the tasks or activities in the month forecasted- no payment will be made for the incomplete task or activity. A task or activity listed must be 100% complete for a payment to be certified.
6. Should the bidder fail to complete the overall project within the fixed duration , the bidder may be liable for penalties per day until completion is reached.
7. Should the bidder fail to price for or sufficiently allow for any risk or unforeseen activities - the risk of such costs shall be carried by the bidder, as all bidders are expected to include the costs and contingencies in its offer.
8. The activity or task deliverable must be available and certified/ accepted by the relevant parties for payment to proceed. IF a deliverable is not complete or is in progress , it will not be paid for until complete.
9. Activities and tasks are priced for the total task and activity as a lump sum therefore no unit of measure is included. There are no interim progress payment unless the interim is defined as a sub task or subactivity and priced as a separate line item.

## Activity Schedule Template
ANNEXURE D: ACTIVITY SCHEDULE
APPROVAL OF THE PROCUREMENT STRATEGY FOR THE APPOINTMENT OF A FIXED AND FIRM TURNKEY CONTRACTOR FOR THE DESIGN AND CONSTRUCTION OF A NEONATAL MODULAR STRUCTURE AT TSHILIDZINI REGIONAL HOSPITAL IN LIMPOPO PROVINCE.
**PROFESSIONAL SERVICES and PRELIMINARY AND GENERAL are minimum items to be priced (Color - ORANGE ) **CONSTRUCTION section serves as a guide for activities to be priced. (Color - BLUE) . The bidder is required to expand on this section ! |  |  | Project Programme (5 Months ) and Activity Payment Schedule
NEONATAL MODULAR STRUCTURE
Scope of Works | Item No | Activity Description | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Total Price Excluding VAT
As per the scope of work documents | 1 | PROFESSIONAL SERVICES
Provide an amount for consultancy and/or design services by professional service providers to cater for the following disciplines: Architectural, QS, Project Manager, Electrical Engineer, Mechanical Engineer and Civil/Structural Engineer (incl. Geotech) as and when required to the approval of the DBSA representative. Please include an amount for as-built drawings.
| 1.1. | Main Task Stage 1 - Initiation
| 1.1.2 | Subtasks ( Inception Report) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.2.1 | Preliminary Environmental Impact Assesstment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.2.2 | Local and statutory Consultations and Approvals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.1.2.3 | Site Constraints | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Geotechnical Investigations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Baseline Environmental Impact Assesments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.2. | Main Task Stage 2 - Concept
| 1.2.1 | Concept Report from all disciplines | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conceptual Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.3. | Main Task Stage 3 - Design Development
| 1.3.1 | Design Development Report | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| 1.4. | Main Task Stage 4 - Design Documentation
| 1.4.1 | Detailed Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.5. | Main Task Stage 5 - Works
| 1.5.1 | Subtasks ( Progress Monitoring and Quality Checks ) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.6 | Main Task Stage 6 - Handover
| 1.6.1 | Subtasks ( Site Handover) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1.7 | Main Task Stage 7 - Close-out
| 1.7.1 | Subtasks ( Close-out report) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | PRELIMINARY AND GENERAL
These preliminary and general items apply to the entire scope of works
| 1 | Site Establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Site De-establishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Temporary works & plant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Security of the works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Insurance & Guarantees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | Contractor's Representatives | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | Compliance with Health, Safety & Occupational Requirements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Enterprise Development of Targeted Enterprise or JV partners | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In 8: Newly added as per CIDB B.U.I.L.D Programme. The rates illustrated are the recommended rates to guide the Employer to determine the amount for Enterprise Development per targeted enterprise. The Employer may adjust these rates which may be affected by factors such as location of the project. The Employer must include this amount as a Provisional Sum in the Preliminary and General (P&G) section as illustrated .
| 8.1 | The contractor shall appoint an Enterprise Development Coordinator (Tender Volume 3, Clause 3.1) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8.2 | Needs Analysis and Enterprise Development Plan per Targeted Enterprise (fixed provisional sum) | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | Item 8.2 refers to the Needs Analysis the contractor shall perform on the targeted enterprise and or JV partner to identify the developmental goals at a rate of R 5000 00 (five thousand rands per targeted enterprise
| 8.3 | Monitoring and Interim reporting per targeted enterprise (fixed provisional sum) | 5714.2857 | 5714.2857 | 5714.2857 | 5714.2857 | 5714.2857 | 5714.2857 | 5714.2857 | 40000 | Item 8.3 refers to the Monitoring and Interim reporting to be performed by the contractor as per the Standard at a rate of R 20 000 00 (twenty thousand rands) per quarter. Business to decide how many quarters are applicable and quantify by R20k and add the total in as a provisional sum. Ive provisionaly indiated it at 1 enterprise at 4 quarters = 1 year
| 8.4 | Project Completion report per Targeted Enterprise (fixed provisional sum) | 0 | 0 | 0 | 0 | 5000 |  |  | 5000 | Item 8.4 refers to the Completion report, the contractor shall submit the Completion report to the Employer’s representative as per the Standard at a rate of R 5000 00 (five thousand rands) per targeted enterprise
0
| 3 | CONSTRUCTION
Bidders are required to make reference to the specifications for the full extent of the works required to be done under each of the trade activities listed in this activity schedule. Bidders are responsible for exapnding on the examples listed below for programming, pricing, cashflow and payment purpose.
| 1 | Alterations | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 2 | Demolitions | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 3 | Substructure | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 4 | Ground floor | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 5 | Structural frame | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 6 | External Façade | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 7 | Roofs | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 8 | Internal Divisions | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 9 | Partitions | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 10 | Floor Finishes | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 11 | Internal Wall Finishes | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 12 | Ceiling Finishes | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 13 | Fittings | 0 | 0 | 0 | 0 | 0 |  |  | 0
0
| 14 | Electrical Installation | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 15 | Plumbing | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 16 | Fire protection | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 17 | Balustrading, handrails, etc | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 18 | Miscellaneous items | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 19 | Specialist fire protection systems | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 20 | Conveyance systems | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 21 | Air conditioning | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 22 | Ventilation | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 23 | Heating and cooling | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 24 | Special electrical systems | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 25 | Electronic systems | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 26 | Other services | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 27 | Communication & Security | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 28 | Signage | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 29 | Artwork, furnishings, etc | 0 | 0 | 0 | 0 | 0 |  |  | 0
| 30 | External Works | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  |  | 10714.2857 | 5714.2857 | 5714.2857 | 5714.2857 | 10714.2857 | 5714.2857 | 5714.2857 | 50000
SUB-TOTAL A (Excl. CSDG, Contingency and VAT) |  |  | 50000 |  |  |  | Total Check |  |  | 0
CIDB minimum Contract Skills Development Goal (CSDG) sum = 0,5% x Subtotal of the tender amount |  |  | 250
SUB-TOTAL B (Incl. CSDG and Excl. Contingency and VAT) |  |  | 50250
Allow Contingencies/ Risk Allowances from Risk Register or 15% of Total |  |  | 1
SUB-TOTAL B (Incl. CSDG and Contingency and Excl. VAT) |  |  | 50251
Add VAT @ 15% |  |  | 7537.65
GRAND TOTAL (Incl. CSDG and Contingency and VAT) |  |  | 57788.65
|  | TOTAL FIXED AND FIRM OFFER | 57788.65
This line /row should give us the total payment in the month , for all the required activities / main tasks achieved.
Suggested the contractor price contingencies on a risk register on the next sheet due to the lump sum contract needing to be fixed and firm - otherwise a maximum of 15% to be allowed.
The activities and task listed herein are examples only ! THE BIDDER MUST DEFINE AND PROGRAMME ALL THE ACTIVITIES AND TASKS REQUIRED TO COMPLETE THE WORKS. THe bidder must therefore expand on this side and ensure the price for the task or activity is populated in the correct month on the payment schedule ( green cells on the right) .

## Risks_Contingencies with Prices
No. | Risk | Impact ( High, Low,Moderate) | Likelihood ( High, Low,Moderate) | Cost Estimate for Risk / Allowance | Comment
1. | Adverse Ground Conditions ( Delete this example) as a result of detailed geotech studies | High | Low | 1 | Asssuming worst case scenario - if piling required
2. | Adverse weather conditions | Low | Low | 0 | No cost for weather conditions, rain during winter is minimal , time risk considered in the 5 month duration.
TOTAL CONTINGENCY/ RISK ALLOWANCE |  |  |  | 1
This is just an example , the bidder must delete and populate correctly