## Drawings Submittals Log
Color Coding
No Action
On Progress
KZN/DOE:KZN-DoE/ STOME DAMAGE REPAIRES PROGRAMME - EZAKHELENI PS - DRAWING REGISTER | [10 empty] | Delayed
[8 empty] | Date: | 2022-09-11 |  | Closed
# | Size | Submittal Sequential No. | Rev. | Trade | Description | Planned Sub.Date | Actual Sub.Date | Returned Date | Action Code | Status | Remarks
A |  | ARCHITECTURAL DRAWINGS
|  | SITE DEVELOPMENT PLAN (SDP) |  |  | DATE OF COMPLETION
1 | A0 | KZN.DoE/ DBSA-BPP-EPS-L-001-0A | 0A | ARCH. | CIRCULATION, EXISTING AND PROPOSED NEW STRUCTURES. | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
|  | BLOCK A: GATE HOUSE |  |  | DATE OF COMPLETION
2 | A1 | KZN.DoE/ DBSA-BPP-EPS-A-L&S-002-0A | 0A | ARCH. | PLAN, SECTION, ELEVATION, SPECS, SCHEDULES and JOINERY. | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
3 | A1 | KZN.DoE/DBSA-BPP-EPS-A-D&S-003-0A | 0A | ARCH. | GATE, FENCE DETAILS, FLAG DETAILS and SPECIFICATIONS | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
|  | BLOCK B: MEDIA CENTRE (LIBRARY and COMP. ROOM) + X1 CLASSROOMS |  |  | DATE OF COMPLETION
4 | A1 | KZN.DoE/ DBSA - BPP- EPS- B- L-004-0A | 0A | ARCH. | PLAN, SECTION, ELEVATION and SPECIFICATIONS | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
5 | A1 | KZN.DoE/ DBSA-BPP- EPS- B- L&F-005-0A | 0A | ARCH. | TILLING & CEILING LAYOUT, WINDOW and DOOR SCHEDULE. | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
6 | A1 | KZN.DoE/ DBSA-BPP- EPS- B- D-006-0A | 0A | ARCH. | COMPUTER ROOM JOINERY DETAILS | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
7 | A1 | KZN.DoE/ DBSA-BPP- EPS- B- D-007-0A | 0A | ARCH. | COMPUTER ROOM JOINERY DETAILS | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
8 | A1 | KZN.DoE/ DBSA-BPP- EPS- B- D-008-0A | 0A | ARCH. | LIBRARY JOINERY DETAILS. | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
9 | A1 | KZN.DoE/ DBSA-BPP- EPS- B- D-009-0A | 0A | ARCH. | CEILING MESH DETAILS and STORE ROOM DETAILS. | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
|  | BLOCK C: SNP KITCHEN |  |  | DATE OF COMPLETION
10 | A0 | KZN.DoE/ DBSA -BPP-EPS-C-L&F-010-0A | 0A | ARCH. | PLAN, SECTION, ELEVATIONS, GENERAL SPECIFICATIONS and CEILING LAYOUTS. | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
11 | A0 | KZN.DoE/ DBSA-BPP-EPS-C-S&F-011-0A | 0A | ARCH. | WINDOW & DOORS SCHEDULE and GENERAL SPECIFICATIONS | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
12 | A1 | KZN.DoE/ DBSA -BPP-EPS-C-JD-012-0A | 0A | ARCH. | TIMBER JOINERY DETAILS. | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
|  | BLOCK D: GIRLS TOILETS |  |  | DATE OF COMPLETION
13 | A1 | KZN.DoE/ DBSA-BPP-BPS-D-L&D-013-0A | 0A | ARCH. | PLAN, SECTION, ELEVATIONS, SPEC'S, SCHEDULES, DETAILS and SANITARY SCHEDULE, ETC. | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
|  | BLOCK E: EDUCATOR'S TOILETS |  |  | DATE OF COMPLETION
14 | A1 | KZN.DoE/ DBSA-BPP-BPS-E-L&D-014-0A | 0A | ARCH. | PLAN, SECTION, ELEVATIONS, SCHEDULES and SPECIFICATIONS | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
B |  | CIVIL AND STRUCTURAL
15 | A1 | P2206/10 - 01 | OA | CIVIL | BLOCK A FOUNDATION AND SURFACE BEDS LAYOUT | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
16 | A1 | P2206/10 - 02 | OA | CIVIL | ABLUTION BLOCK C AND D FOUNDATION AND SURFACE BEDS | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
17 | A1 | P2206/10 - 03 | OA | CIVIL | BLOCK D AND E FOUNDATION AND SURFACE BEDS LAYOUT | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
18 | A1 | P2205/90 - 04 | OA | CIVIL | HARD SURFACE AND STORMWATER LAYOUT | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
C |  | ELECTRICAL
19 | A1 | 2210 - EL,EP - 01 | 0A | ELECT | MEDIA BLOCK LIGHTING AND SMALL POWER LAYOUT | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
20 | A1 | 2210 - EL,EP - 02 | OA | ELECT | KITCHEN BLOCK LIGHTING AND SMALL POWER LAYOUT | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
21 | A1 | 2210 - EL,EP - 03 | OA | ELECT | GUARD HOUSE BLOCK LIGHTING AND SMALL POWER LAYOUT | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
22 | A1 | 2210 - EL,EP - 04 | OA | ELECT | ABLUTION BLOCK LIGHING LAYOUT | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
23 | A1 | 2210 - ESCH - 00 | OA | ELECT | SCHEMATICS | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
24 | A1 | 2210 - ESP - 00 | OA | ELECT | SITE PLAN LAYOUT | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete
25 | A1 | 2210 - LPE - 00 | OA | ELECT | OVERALL SITE LIGHTNING PROTECT LAYOUT | 30 AUG. 22 | 27 AUG. 22 | N/A | N/A | 100% Complete