## Drawings Submittals Log
Color Coding
No Action
On Progress
KZN/DOE:KZN-DoE/ STOME DAMAGE REPAIRES PROGRAMME - EXHAPHOZINI PS DRAWING REGISTER | [10 empty] | Delayed
[8 empty] | Date: | 2022-09-10 |  | Closed
# | Size | Submittal Sequential No. | Rev. | Trade | Description | Planned Sub.Date | Actual Sub.Date | Returned Date | Action Code | Status | Remarks
A |  | ARCHITECTURAL DRAWINGS
|  | SITE DEVELOPMENT PLAN (SDP) |  |  | DATE OF COMPLETION
1 | A0 | KZN.DoE/DBSA-BPP-BPS-EPS -L-001-0A | 0A | ARCH. | CIRCULATION, EXISTING AND PROPOSED NEW STRUCTURES. | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
|  | BLOCK A: GATE HOUSE |  |  | DATE OF COMPLETION
2 | A1 | KZN.DoE/ DBSA-BPP-EPS-A-L&S-002-0A | 0A | ARCH. | PLAN, SECTION, ELEVATION, SPECS, SCHEDULES and JOINERY. | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
3 | A1 | KZN.DoE/DBSA-BPP-EPS-A-D&S-003-0A | 0A | ARCH. | GATE, FENCE DETAILS, FLAG DETAILS and SPECIFICATIONS | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
|  | BLOCK B: SNP KITCHEN |  |  | DATE OF COMPLETION
4 | A1 | KZN.DoE/ DBSA - BPP- EPS- B- L-004-0A | 0A | ARCH. | PLAN, SECTION, ELEVATION and SPECIFICATIONS | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
5 | A1 | KZN.DoE/ DBSA-BPP- EPS- B- L&F-005-0A | 0A | ARCH. | TILLING & CEILING LAYOUT, WINDOW and DOOR SCHEDULE. | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
6 | A1 | KZN.DoE/ DBSA-BPP- EPS- B- D-006-0A | 0A | ARCH. | COMPUTER ROOM JOINERY DETAILS | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
|  | BLOCK C: X4 CLASS ROOMS and TOILETS |  |  | DATE OF COMPLETION
7 | A1 | KZN.DoE/ DBSA-BPP-EPS-C-L&S-07-0A | 0A | ARCH. | PLAN, SECTION, ELEVATIONS, WINDOW & DOOR SCHEDULE. | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
8 | A1 | KZN.DoE/ DBSA-BPP-EPS-C-F&S-008-0A | 0A | ARCH. | SPECIFICATIONS, TILLING and CEILING LAYOUTS. | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
|  | BLOCK D: GRADE R FACILITIES |  |  | DATE OF COMPLETION
9 | A1 | KZN.DoE/ DBSA-BPP-EPS-D-L-009-0A | 0A | ARCH. | PLAN, SECTION and ELEVATIONS | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
10 | A1 | KZN.DoE/ DBSA-BPP-EPS-D-S&F-010-0A | 0A | ARCH. | CEILING LAYOUT, TILLING LAYOUT, WINDOW and DOOR SCHEDULE. | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
11 | A1 | KZN.DoE/ DBSA-BPP-EPS-D-D-011-0A | 0A | ARCH. | TIMBER JOINERY DETAILS | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
B |  | CIVIL AND STRUCTURAL
12 | A1 | P2205/90-01 | 0A | CIVIL | HARD SURFACE AND STORMWATER LAYOUT | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
13 | A1 | P2206/10-01 | 0A | CIVIL | KITCHEN AND GUARD HOUSE FOUNDATION AND SLAB LAYOUT | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
14 | A1 | P2206/10-02 | 0A | CIVIL | FOUR CLASSROOM FOUNDATION AND SLAB LAYOUT | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
15 | A1 | P2206/10-03 | 0A | CIVIL | GRADE R FOUNDATION AND SLAB LAYOUT | 31 AUG. 22 | 28 AUG. 22 | N/A | N/A | 100% Complete
C |  | ELECTRICAL DRAWING
16 | A1 | 2209 - EL,EP - 01 | 0A | ELEC | FOUR CLASSROOM BLOCK LIGHT AND POWER LAYOUT | 31 AUG. 22 | 10 SEP,22 | N/A | N/A | 100% Complete
17 | A1 | 2209 - EL,EP - 02 | 0A | ELEC | KITCHEN BLOCK LIGHT AND POWER LAYOUT | 31 AUG. 22 | 10 SEP,22 | N/A | N/A | 100% Complete
18 | A1 | 2209 - EL,EP - 03 | 0A | ELEC | GRADE R BLOCK LIGHT AND POWER LAYOUT | 31 AUG. 22 | 10 SEP,22 | N/A | N/A | 100% Complete
19 | A1 | 2209 - EL,EP - 04 | 0A | ELEC | GUARD HOUSE LIGHT AND POWER LAYOUT | 31 AUG. 22 | 10 SEP,22 | N/A | N/A | 100% Complete
20 | A1 | 2209 - ESP - 00 | 0A | ELEC | SITE PLAN ELECTRICAL LAYOUT | 31 AUG. 22 | 10 SEP,22 | N/A | N/A | 100% Complete
21 | A1 | 2209 - LPE - 00 | 0A | ELEC | OVERALL SITE LIGHTING LAYOUT | 31 AUG. 22 | 10 SEP,22 | N/A | N/A | 100% Complete